## Project Planner
Sydney Airbnb Data Analysis Project
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 10 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | INITIATION | 1 | 14 | 4 | 11 | 0%
1.1 | Define Project Scope and Objectives | 1 | 7 | 4 | 3 | 0%
1.2 | Assign roles to team members | 2 | 1 | 5 | 2 | 0%
1.3 | Develop project management plan | 4 | 7 | 11 | 2 | 0%
1.4 | Risk management | 1 | 49 |  |  | 0%
1.5 | Outline User Requirements | 8 | 7 | 11 | 3 | 0%
1.6 | Outline Software Requirements | 8 | 7 | 11 | 3 | 0%
2 | DATA COLLECTION | 8 | 14 |  |  | 0%
2.1 | Obtain Sydney AirBnB dataset | 8 | 1 |  |  | 0%
2.2 | Risk management plan | 9 | 1 |  |  | 0%
2.3 | Project cost estimate | 10 | 1 |  |  | 0%
2.4 | Project timeline | 11 | 3 |  |  | 0%
2.5 | Clean and preprocess the data | 15 | 5 |  |  | 0%
2.5.1 | Validate data | 15 | 3 |  |  | 0%
2.5.2 | Handle missing values | 18 | 2 |  |  | 0%
2.5.3 | Format data for analysis | 20 | 2 |  |  | 0%
3 | CREATION | 15 | 28 |  |  | 0%
3.1 | Software Design flowchart/plan | 15 | 4 |  |  | 0%
3.2 | Identify System components/functions | 19 | 3 |  |  | 0%
3.3 | Suburb Specific Listing information | 22 | 5 |  |  | 0%
3.3.1 | Design Search Functionality | 22 | 3 |  |  | 0%
3.3.2 | Implement/Test algorithm | 25 | 2 |  |  | 0%
3.4 | Price Distribution task | 25 | 4 |  |  | 0%
3.4.1 | Extract price data for chart | 25 | 2 |  |  | 0%
3.4.2 | Design and generate chart | 27 | 2 |  |  | 0%
3.5 | Keyword-based Search | 28 | 4 |  |  | 0%
3.5.1 | Design search functionality | 28 | 2 |  |  | 0%
3.5.2 | Implement algorithm | 30 | 1 |  |  | 0%
3.5.3 | Test and validate algorithm | 31 | 1 |  |  | 0%
3.6 | Cleanliness Analysis | 30 | 4 |  |  | 0%
3.6.1 | Extract Customer Reviews Data | 30 | 1 |  |  | 0%
3.6.2 | Identify cleanliness related words | 32 | 2 |  |  | 0%
3.6.3 | Quantify frequency of keywords | 33 | 2 |  |  | 0%
3.7 | Suburb Cost/Rating Analysis | 32 | 4 |  |  | 0%
3.7.1 | Extract review price/rating | 32 | 1 |  |  | 0%
3.7.2 | Test and validate algorithm | 32 | 2 |  |  | 0%
3.7.3 | Display data visually | 33 | 2 |  |  | 0%
3.8 | User interface design | 36 | 7 |  |  | 0%
3.8.1 | Structural Design | 36 | 4 |  |  | 0%
3.8.2 | Visual Design | 39 | 4 |  |  | 0%
4 | VALIDATION | 43 | 4 |  |  | 0%
4.1 | Analyse insights | 43 | 2 |  |  | 0%
4.2 | Test full program functionality | 44 | 3 |  |  | 0%
4.2.1 | Identify & address bugs and issues | 44 | 2 |  |  | 0%
4.2.2 | Create use cases for software | 45 | 2 |  |  | 0%
5 | CLOSURE | 46 | 4 |  |  | 0%
5.1 | Review project against initial objectives | 46 | 1 |  |  | 0%
5.2 | Handover Final Software Version | 47 | 1 |  |  | 0%
5.3 | Software Testing Report | 48 | 2 |  |  | 0%